CNAP CENTER  ·  PHASE S (COBRE-S) APPLICATION  ·  PAR-27-055

Assignments and Notes

CN Core  ·  Heather Bailey, Core Director

| Milestone | Day | Month | Date | Notes |
| --- | --- | --- | --- | --- |
| Work starts | Fri | Oct | 30 | 2026 |
| Your first deadline | Fri | Nov | 13 |  |
| Your last deadline | Fri | Jan | 15 |  |
| Application fully complete | Fri | Jan | 15 | 2027 (K-State is closed Mon, Jan 18) |
| NIH due date | Mon | Jan | 25 | 2027, 5:00 PM local time |

YOUR LINKS:

| Link | Click to open | What it's for |
| --- | --- | --- |
| Smartsheet | Open Smartsheet | Your assignments, directions, deadlines, and status |
| Working drafts (Dropbox) | WORKING DRAFTS › CN Core | Where you write and revise |
| Final versions (Dropbox) | FINAL VERSIONS › CN Core | Approved, submission-ready documents only |
| 2021, Phase 2 Proposal Materials | Open in Dropbox | If helpful to reflect on what was said or done previously. |
| Your 2025 Phase 3 Materials | Open in Dropbox | If helpful to reflect on what you wrote last year toward the outdated Notice of Funding Opportunity. |

RULES TO KEEP IN MIND:

## Page limits

- Specific Aims: 1 page.

- Research Strategy: 6 pages.

- Project Summary/Abstract: 30 lines of text.

- O&M Plan input: becomes part of the Center Research Strategy, which has 12 pages for Sections A–E combined.

## The order of the work

- Aims first. You share the Center's draft Specific Aims with the Core Directors Fri, Nov 6. The CN Core's Specific Aims are due Fri, Nov 13.

- Consider writing the strategy before the budget. The Research Strategy is due Mon, Nov 30, and the Budget and Budget Justification are ready for Roxana's review Fri, Dec 4. The budget costs out what the strategy describes.

## Reviews before submission

- Budget review: Roxana (CNAP's budget reviewer) first, then Tim in Central Office. Your revised (final) budget is ready for her review the morning of Fri, Jan 15.

- Outside scientific review: your Specific Aims and Research Strategy go to an external reviewer Mon, Dec 7. Must-fix revisions are due Mon, Jan 11, with no scope or budget changes.

- Biosketch review: Kim in Central Office reviews your one biosketch; its dates are in your Center Director packet.

## Phase S rules for your core (NOFO)

- Phase S sustains, modernizes, and consolidates the cores CNAP already has.

- No duplicate services, and open to others. The core can't duplicate services already at K-State, and it must be available to other K-State investigators and to other IDeA-state institutions.

- Serve the Scientific Research Program (SRP) Core. The core supports the projects led by SRP Investigators (SIs). Reviewers look for how it meets the SRP Core's needs.

- Budget: five years; no Alterations & Renovations allowed in a Research Core.

## What doesn't go in your core (NOFO)

- Letters of support. All support goes in the single Institutional Letter in the Center (Overall).

- Data Management and Sharing Plan. It goes in the Center (Overall) only.

- Project Narrative. Center (Overall) only.

- Appendix: optional and limited to specific item types; most applications include none. If your core needs one, tell Morgan by Fri, Dec 11 (CNAP).

## Your 13 steps at a glance:

| CNAP Internal Due Date |  |  | Step | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Fri | Nov | 13 | 1. CN Core Specific Aims | 1 page | — |
| Wed | Nov | 18 | 2. CN Core input to the Center's O&M Plan | 12 pages for Sections A–E combined | Morgan (combines into final plan) |
| Mon | Nov | 30 | 3. CN Core Research Strategy | 6 pages | — |
| Fri | Dec | 4 | 4. CN Core Budget + Budget Justification | Form entries + justification | Roxana (reviews) |
| Mon | Dec | 14 | 5. CN Core Equipment | No limit | — |
| Wed | Dec | 16 | 6. CN Core Facilities & Other Resources | No limit | — |
| Thu | Dec | 17 | 7. CN Core Resource Sharing Plan | No limit | — |
| Thu | Dec | 17 | 8. Your biosketch: review draft (the same one as in your Center Director packet) | Set by SciENcv format | Morgan (checks format); Kim (reviews) |
| Wed | Jan | 6 | 9. CN Core Bibliography & References Cited | No limit | — |
| Mon | Jan | 11 | 10. CN Core: revise Specific Aims + Research Strategy, must-fix items only | Same as originals | — |
| Tue | Jan | 12 | 11. CN Core Project Summary/Abstract | 30 lines of text | — |
| Wed | Jan | 13 | 12. Your biosketch: final (the same one as in your Center Director packet) | Set by SciENcv format | Morgan (checks format); Kim (reviews) |
| Fri | Jan | 15 | 13. CN Core: revised (final) Budget + Budget Justification | — | Roxana (reviews) |

# Our Workflow: Smartsheet and Dropbox

Submission workflow, in brief. The full instructions are in your Proposal Packet (Submission Workflow and File Management).

## Why Smartsheet

- Smartsheet is the live version of this packet. Dates, links, and assignments are updated there first, so if Smartsheet and this packet ever differ, Smartsheet wins.

## How to use it

- Find your rows in Smartsheet: filter by your name in the Assigned To column.

- Open what you need from your row: your directions (this packet), your WORKING DRAFTS folder, your FINAL VERSIONS folder, and reference materials such as prior COBRE proposals.

- Update your status from the Status drop-down as you work. Setting Ready for Review tells your reviewer the draft is waiting.

- Due date definition: Please save your working draft in your WORKING DRAFTS folder by the internal due date.

- Add the deadlines to your calendar: subscribe to the Smartsheet calendar in Outlook or Google Calendar, and date changes update automatically.

- Getting in: accept the invitation email and sign in with your K-State account. The mobile app works too.

### Smartsheet statuses

| Status | What it means |
| --- | --- |
| Not Started | Work has not yet begun. |
| In Progress | The contributor is actively developing the component. |
| Ready for Review | The working draft is ready for review by the designated reviewer. |
| Revisions Requested | Additional revisions are needed before approval. |
| Approved / Ready for Finalization | The component has completed the required review and is approved to move into the finalization process. |
| Finalized | The approved, submission-ready document has been placed in the FINAL VERSIONS folder and verified by the Admin Core. |

Important: Completing a draft does not automatically mean that a component is approved for submission. Only documents that have completed the required review and approval process should be placed in the FINAL VERSIONS folder.

## Where files go (Dropbox)

- WORKING DRAFTS: all writing and revisions are saved here. Start with the applicable NIH-provided form or document, if required; otherwise, create a Word document using the applicable component instructions and formatting guidance.

- FINAL VERSIONS: reserved for documents that have completed the required review and have been approved for inclusion in the submission. Confirm the document is correctly formatted. The Admin Core will coordinate final-document tracking and proposal assembly.

- Reference materials: prior COBRE Phase 2 proposal materials and last year’s Phase 3 draft documents are in the Dropbox (links on page 1). Phase S requirements may differ, so verify current requirements (explained in this packet) before relying on them.

# Specific Aims

One page stating what the CN Core will do over the five years.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Fri | Nov | 13 | CN Core Specific Aims | 1 page | — |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements

- 1 page. Follow NIH's standard Specific Aims instructions; the NOFO adds nothing specific for core Aims.

- Existing core only. No new cores may be established in Phase S. Your aims describe sustaining, modernizing, or consolidating the core CNAP already has.

## CNAP guidance (not NOFO rules)

- Write toward the Center's Aims. You share the draft Center Specific Aims with the Core Directors Fri, Nov 6. Frame the CN Core's aims to support them.

- Set up the Research Strategy. Each of the core's specific aims should map to its part of the strategy (due Mon, Nov 30).

## How reviewers will score it

Reviewers score your core with five questions:

- Is the request to support the core well justified?

- Does the core give suitable scientific support to the Center's research area?

- Does the business plan account for future growth in the core's user base and for the core's sustainability (the Phase S question)?

- Does the Core Director have the expertise to oversee maintaining and growing the core's resources and facilities?

- Are there enough institutional commitments to keep the resources and facilities the core needs available?

FOR REFERENCE: THE NOFO'S EXACT WORDS:

### Review criteria

NOFO, Sec. V.1, Review Criteria for Cores › Research Cores

Is the request to support the Research Core well justified? Does the Core provide suitable scientific support to the proposed scientific area of the COBRE? Does the business plan account for future growth in the Core's user base ensuring an expansion of its reach (COBRE-E) and its sustainability (COBRE-S), as applicable? Does the Core Director have the expertise to provide the necessary oversight to administer the maintenance and growth of existing core resources and laboratory facilities to carry out the scientific objectives outlined in the application? Are there sufficient institutional commitments to ensure that the resources and facilities required to sustain and enhance the Core will be available?

# Your core's input to the Center's Organization and Management Plan

A short write-up of how your core fits with K-State's existing resources. You and Morgan fold it into the final Organization and Management (O&M) Plan, Section B of the Center Research Strategy (final due Mon, Nov 30).

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Wed | Nov | 18 | CN Core input to the Center's O&M Plan | 12 pages for Sections A–E combined | Morgan (combines into final plan) |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements (for the O&M Plan as a whole)

- Each component's contribution. How each part of the Center contributes to its goals and works with the other parts.

- No duplication. How each Research Core fits with existing resources at K-State without duplicating them, including equipment, instrumentation, and cores supported by current or prior IDeA awards (COBRE, INBRE, or CTR).

## What to write for the CN Core

- What your core offers that isn't available elsewhere at K-State.

- What it works alongside: the existing equipment, instruments, and IDeA-supported cores it complements.

- How it connects to the SRP Core and to the other cores.

## CNAP guidance (not NOFO rules)

- Page limit. The Center Research Strategy has 12 pages for Sections A–E combined, so keep your input brief; you and Morgan will trim it to fit.

## How reviewers will score it

- Does the O&M Plan give confidence that the Center's overall goals will be achieved?

FOR REFERENCE: THE NOFO'S EXACT WORDS:

NOFO, Sec. IV.2, Overall Component › PHS 398 Research Plan › Research Strategy › B. Organization and Management Plan

The Organization and Management Plan for the Center should clearly convey a strategy that demonstrates an effective use of the available funding, the proposed configuration of the Center and its cores, and the approaches to expand (COBRE-E) or sustain (COBRE-S) biomedical research capacity. Describe:

- How each of the Center's components will contribute to the Center's goals and synergize with each other, and

- How the proposed Research Cores (if applicable) fit with existing resources at the organization without being duplicative; include equipment, instrumentation, and cores supported by current or prior IDeA (COBRE, INBRE, or CTR) awards.

### Review criteria

NOFO, Sec. V.1, Scored Review Criteria - Overall › Approach

Does the Organization and Management Plan provide confidence that the overall goals of the Center will be achieved?

# Research Strategy

The main description of the CN Core: what it provides, who uses it, and how it will be sustained.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Mon | Nov | 30 | CN Core Research Strategy | 6 pages | — |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements: describe and justify

- How the core's resources support the Center's science, plus other related research resources already at K-State.

- The technology, instruments, and services the core will provide.

- Instruments, equipment, or changes to existing core facilities. Account for K-State's current infrastructure and services related to the request.

- The core's contribution: how it expands research, the service it provides to meet the SRP Core's needs, and its sustainability.

- The core's user base and any plans to expand it.

- The business plan: how service requests are prioritized, the user fee structure, and maintenance costs.

## Restrictions

- 6 pages.

- No new cores in Phase S. Describe the existing core being sustained, modernized, or consolidated.

- No duplicate services. A core that duplicates services already available at K-State isn't allowed.

- Open to others. The core must be available to other K-State investigators and to investigators at other IDeA-state institutions.

## Encouraged by the NOFO

- Building on what exists: using, modifying, or expanding existing core resources supported by institutional funds or other IDeA programs.

- Consolidation and sharing: consolidating existing cores (for technology advancement or administrative efficiency) and sharing facilities supported by other IDeA programs (INBRE, CTR, and other COBREs).

## CNAP guidance (not NOFO rules)

- Write strategy before budget. The budget (due Fri, Dec 4) costs out what the strategy describes. A budget line with no matching activity here will be flagged.

- Frame growth around sustainability. Growing the user base or services isn't prohibited; tie it to keeping the core running after COBRE support ends.

- Answer the five review questions directly, especially the business plan and institutional commitments.

## How reviewers will score it

- Is the request to support the core well justified?

- Does the core give suitable scientific support to the Center's research area?

- Does the business plan account for future growth in the core's user base and for the core's sustainability (the Phase S question)?

- Does the Core Director have the expertise to oversee maintaining and growing the core's resources and facilities?

- Are there enough institutional commitments to keep the resources and facilities the core needs available?

FOR REFERENCE: THE NOFO'S EXACT WORDS:

NOFO, Sec. IV.2, Research Core › PHS 398 Research Plan › Research Strategy

Research Strategy: Describe and justify:

- How the Core's resources will be used to support the scientific breadth of the Center. Applicants should also describe other related research resources already available at the applicant organization,

- The technology, instrumentation, and/or services the Core will provide,

- Instruments, equipment or modification of existing core facilities. Account for the organization's current infrastructure and offered services pertinent to the request,

- The contribution of the Core as it expands research, the service it would provide to meet the needs of the SRP, and its sustainability,

- The Core's user base and any plans for its expansion, and

- The business plan for operation of the Core, including prioritization of service requests, user fee structure, and maintenance costs.

NOFO, Sec. IV.2, Research Core (component preamble)

Research Cores should be made available to other investigators at the institution as well as those from other IDeA state institutions. Cores that duplicate services already available at the applicant institution are not allowed. Utilization, modification, or expansion of existing Core resources supported by institutional funds or other IDeA programs to accomplish the goals of proposed COBRE research is strongly encouraged.

NOFO, Sec. I (Research Core(s), optional)

No new cores may be established in the COBRE-S phase. The consolidation of existing Cores for technology advancement and/or administrative efficiency and the sharing of research facilities supported by other IDeA programs (e.g., INBRE, CTR, and other COBREs) is strongly encouraged.

### Review criteria

Review questions for this piece are quoted in full under “Specific Aims”.

# Budget and Budget Justification

The CN Core's five-year budget (entered as forms) and the written justification for each cost.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Fri | Dec | 4 | CN Core Budget + Budget Justification | Form entries + justification | Roxana (reviews) |
| Fri | Jan | 15 | CN Core: revised (final) Budget + Budget Justification | — | Roxana (reviews) |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements

- Five years. A detailed budget for the entire project period.

- Justification. The NOFO adds no special justification instructions, so NIH's standard (SF424 R&R) instructions apply.

## What a Research Core can pay for

- Personnel and supplies.

- New equipment and modernizing instruments.

- Using, modifying, or expanding existing resources needed for the Center's scientific goals.

## Restrictions

- No Alterations & Renovations (A&R) in a Research Core.

- No new cores. The NOFO's budget text is shared with Phase E; its wording about establishing Research Core facilities applies only to Phase E.

- Total cap. All of the Center's budgets together must not exceed $1.5 million in direct costs per year (consortium F&A excluded). Roxana tracks the total.

## CNAP guidance (not NOFO rules)

- Every cost traces to the Research Strategy. Each budget line should match an activity the strategy describes.

- Frame costs for Phase S: sustaining, modernizing, or consolidating the existing core.

- Justify each year: personnel, supplies, equipment purchases or modernization, and core operations.

## Review timeline (CNAP)

- Fri, Dec 4: Budget and Budget Justification in WORKING DRAFTS, status Ready for Review. Roxana reviews them Dec 7–11 and sends any fixes back to you.

- Mon, Dec 14: Roxana sends every budget to Tim in Central Office. Tim reviews for at least two working weeks and may flag issues as he finds them; fix each one as it reaches you.

- Fri, Jan 8: All of Tim's comments are back.

- Fri, Jan 15 (morning): Your revised (final) budget and justification in WORKING DRAFTS, status Ready for Review. Roxana checks them and sends the final budgets to Tim that day. After this, critical edits only.

- Tue, Jan 19: Morgan uploads the final budgets to Cayuse (K-State is closed Mon, Jan 18).

## How reviewers will score it

- Reviewers consider whether the budget and the requested period of support are fully justified and reasonable for the proposed research.

FOR REFERENCE: THE NOFO'S EXACT WORDS:

NOFO, Sec. IV.2, Research Core › Budget (Research Core)

Funds may be requested to establish Research Core facilities and/or to use, modify, or expand existing resources that are necessary for accomplishing the scientific goals of the Center. In addition to personnel and supply costs, the acquisition of new equipment and modernization of instrumentation may be proposed. Alteration and Renovation (A&R) of core facilities cannot be proposed under this component.

Core facilities should have a detailed budget for the entire proposed project period (five years).

### Review criteria

NOFO, Sec. V.1, Additional Review Considerations - Overall › Budget and Period of Support

Reviewers will consider whether the budget and the requested period of support are fully justified and reasonable in relation to the proposed research.

# Equipment

A list of the major equipment already available for this work.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Mon | Dec | 14 | CN Core Equipment | No limit | — |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements

- Standard NIH instructions apply. The NOFO adds nothing specific for this attachment.

## What to include (NIH's instructions, paraphrased)

- Major equipment already available for the project.

- Where it is and what it can do, when that's helpful.

## CNAP guidance (not NOFO rules)

- Existing equipment only. Equipment you plan to buy belongs in the budget, not here.

- Match the Research Strategy. Name the same instruments the strategy relies on, using the same names.

## How reviewers will score it

This attachment supports the Center's Environment score:

- Will the scientific environment contribute to the Center's success?

- Does the application show K-State's commitment to strengthening research capacity in the Center's area?

- Are the existing physical resources adequate for the Center's goals?

- Is the existing pool of potential SRP Investigators (SIs) broad and well integrated?

- How well do the plans show the need for support to sustain existing resources and future growth (the Phase S question)?

FOR REFERENCE: THE NOFO'S EXACT WORDS:

### Review criteria

NOFO, Sec. V.1, Scored Review Criteria - Overall › Environment

Will the scientific environment in which the work will be done contribute to the probability of success? Does the application demonstrate appropriate institutional commitment to support the goal of strengthening the biomedical research capacity in the scientific area of the Center? Are the existing physical resources available to the investigators adequate to meet the goals of the Center? Is the existing pool of potential SIs, as a whole, scientifically broad and well-integrated to spur research capacity growth in the proposed area of investigation? How effectively do the overall plans convey the need to request support to expand (COBRE-E) or sustain (COBRE-S) existing resources and future growth in the proposed broad area of research, as applicable?

# Facilities & Other Resources

A description of the space, resources, and institutional support behind this work.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Wed | Dec | 16 | CN Core Facilities & Other Resources | No limit | — |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements

- Standard NIH instructions apply. The NOFO adds nothing specific for this attachment.

## What to include (NIH's instructions, paraphrased)

- How the environment will help the work succeed.

- Anything unique about the environment.

- K-State's investment in the work's success.

## CNAP guidance (not NOFO rules)

- Back up the Institutional Letter. Concrete K-State commitments named here (space, staff, institutional funds) strengthen the Environment score.

## How reviewers will score it

- This attachment supports the Center's Environment score (questions listed under Equipment).

FOR REFERENCE: THE NOFO'S EXACT WORDS:

### Review criteria

Review questions for this piece are quoted in full under “Equipment”.

# Resource Sharing Plan

A short plan for sharing research resources produced by the CN Core, or the reason for not sharing them.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Thu | Dec | 17 | CN Core Resource Sharing Plan | No limit | — |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements

- Follow NIH's instructions. The NOFO points to the Resource Sharing Plan instructions in NIH's application guide (SF424 R&R) and adds nothing of its own.

## Restrictions

- No Data Management and Sharing (DMS) Plan in the CN Core. The DMS Plan goes in the Center (Overall) only; Morgan writes it.

## CNAP guidance (not NOFO rules)

- Keep it short and specific. Say which resources the component will share (for example, model organisms, protocols, or tools), how, and when. If there is nothing to share, say so and give the reason.

## How reviewers will score it

- Reviewers comment on whether the Resource Sharing Plan, or the reason for not sharing resources, is reasonable. It is not scored.

FOR REFERENCE: THE NOFO'S EXACT WORDS:

NOFO, Sec. IV.2, Research Core › PHS 398 Research Plan

Resource Sharing Plan: Individuals are required to comply with the instructions for the Resource Sharing Plans as provided in the SF424 (R&R) Application Guide.

NOFO, Sec. IV.2, Research Core › Other Plan(s)

Do not include a Data Management and Sharing (DMS) Plan within this Component. If a DMS Plan is required for this NOFO, it must be included within the Overall Component.

### Review criteria

NOFO, Sec. V.1, Additional Review Considerations - Overall › Resource Sharing Plans

Reviewers will comment on whether the Resource Sharing Plan(s) (e.g., Sharing Model Organisms (https://sharing.nih.gov/other-sharing-policies/model-organism-sharing-policy#policy-overview)) or the rationale for not sharing the resources, is reasonable.

# Your Biosketch

Your one biosketch covers both your Center Director (PD/PI) role and this CN Core role. Upload it once, in the Center (Overall).

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Thu | Dec | 17 | Your biosketch: review draft (the same one as in your Center Director packet) | Set by SciENcv format | Morgan (checks format); Kim (reviews) |
| Wed | Jan | 13 | Your biosketch: final (the same one as in your Center Director packet) | Set by SciENcv format | Morgan (checks format); Kim (reviews) |

## CNAP guidance (not NOFO rules)

- Details live in your Center Director packet: the NOFO's biosketch requirements for the Center Director (PD/PI), your Current & Pending Support, and the review timeline (draft Thu, Dec 17; final Wed, Jan 13).

- Cover the CN Core in the Personal Statement: your expertise in overseeing, maintaining, and growing the core's resources, since reviewers ask that of every Core Director.

# Bibliography & References Cited

The list of references cited in the component's Specific Aims and Research Strategy.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Wed | Jan | 6 | CN Core Bibliography & References Cited | No limit | — |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements

- Standard NIH instructions apply: a bibliography of any references cited. It is a separate attachment and doesn't count toward page limits.

## CNAP guidance (not NOFO rules)

- Numbered style. Use numbered superscript citations in order of first appearance, and a numbered reference list such as NLM (Vancouver), as set out in the Proposal Writing Conventions.

- Include PMCIDs for any cited paper covered by the NIH Public Access Policy.

- One list per component. If your Aims cite papers, number one list across the Aims and the Research Strategy.

- Due Wed, Jan 6, so it reflects the final text; update it if the Jan 11 revisions add or drop a citation.

# Revisions after external review

Changes to the Specific Aims and Research Strategy in response to the external scientific review.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Mon | Jan | 11 | CN Core: revise Specific Aims + Research Strategy, must-fix items only | Same as originals | — |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## CNAP guidance (not NOFO rules)

- Must-fix items only. External reviewer comments are due Mon, Jan 4. You and Morgan sort them into must-fix items by Wed, Jan 6; fix only those.

- No scope or budget changes. Budgets are being finalized Jan 8–15, so don't change anything that would change a budget.

- Same page limits as the originals: Specific Aims 1 page; Research Strategy 6 pages.

- Due Mon, Jan 11, before the Project Summaries (Tue, Jan 12) and the Jan 15 handoff to Central Office.

# Project Summary/Abstract

A 30-line summary of the CN Core.

| CNAP Internal Due Date |  |  | What's due | Page limit | Who else |
| --- | --- | --- | --- | --- | --- |
| Day | Month | Date |  |  |  |
| Tue | Jan | 12 | CN Core Project Summary/Abstract | 30 lines of text | — |

Save it: WORKING DRAFTS › CN Core   ·   Once approved: FINAL VERSIONS › CN Core

## Requirements

- 30 lines of text. Standard NIH instructions apply. The NOFO doesn't exclude a Project Summary from the CN Core, and NIH's validation requires one in every component.

- No Project Narrative in the CN Core. The NOFO says not to complete it, even though the online screens mark it with an asterisk. The Project Narrative goes in the Center (Overall) only.

## CNAP guidance (not NOFO rules)

- Summarize this component only, not the whole Center.

- Write it last. It's due Tue, Jan 12, the day after the external-review revisions, so it matches the final text.

FOR REFERENCE: THE NOFO'S EXACT WORDS:

NOFO, Sec. IV.2, Admin Core / Research Core / SRP › Research & Related Other Project Information

Project Narrative: Do not complete. Note: ASSIST screens will show an asterisk for this attachment indicating it is required. However, eRA systems only enforce this requirement in the Overall component and applications will not receive an error if omitted in other components.